## TP Plan
Main Module | Sub-Module | Approximate UI count | Phase (Each Phase 3 months) | Estimation | Developer Comments
Security | User Authentication, Roles, Privileges, Groups, Users (form, reset password form), My Account, Organizations, Audit Log, Super Admin Billing Module, Signup Page, Trial Signup Page, Forgot Password | 20 | Phase I | 80 | Can use some LDAP open source and integrate it
Customers | Customers, Receivables, Sales Orders, Quotes, Over the counter Sales, Invoices Multi-Invoices, Customer Types, Payment Types, Credit Memos, Debit Memos, Quote Templates, | 24 | Phase I | 360
Vendors | Vendors, Purchase Orders, Consignments, Invoices, Payables, Shipment Settings, Package Settings | 14 | Phase I | 240
Company Master | Chart of Accounts, Tax Territories, Rolodex, Divisions, State Tax Settings, Accounting Cycles, Company Profile | 13 | Phase I | 240
Sales Rep | Commissions, Commission Split Types | 4 | Phase II | 120
Products Module | Warehousing (In and out), Product Catelog, Product Categories, Product Departments, Order Points, Receive Inventory, Transfer Inventory, Count Inventory, Kit Recipes, Assembly Kits | 24 | Phase II | 400
Job Work | Jobs, Bids, Schedule Templates, Submittals, Models | 30 | Phase II | 240
Vendor Reports | about 30 reports |  | Phase II | 120
Finance (Banking) | Banking, General Ledger, Accounts, Journals, | 10 | Phase II | 300
Finance Reports | 10 reports |  | Phase II | 40
Customer Support | Customer Service Requests | 2 | Phase II | 120
Dashboards | Project View, Job View, Home Page | 10 | Phase III | 100 | This should be done right;
Customer Reports | About 20 reports |  | Phase III | 80 | For Reports, we have to use Jasper Reports or Pentaho Reports to save time
Employees | Employees, HR, Payroll | 6 | Phase III | 200
Employee Reports | About 20 reports |  | Phase III | 80
Job Reports | About 30 Reports |  | Phase III | 120
Taxation | Taxation Reports, 1099, 941 forms, W2, W3 forms and more | 16 | Phase III | 120
Company Reports | About 20 reports |  | Phase III | 80
Messages | Messaging Integration | 6 | Phase IV | 40 | We can use some Messaging API and OS code
Document Module | Company Document Repository | 4 | Phase IV | 24 | We can use some open source integration here
Faxes | Fax-Machine Integration | 4 | Phase IV | 40 | We can use some Fax API and open source code
Documents | Import Documents | 3 | Phase IV | 16
Documents | Link External Documents | 3 | Phase IV | 16
3176
173

## TP Status
Task | % Completed | Phase | Impediments/Comments
Analyzing and understanding the the Database and making an ERD | 50% | I | Trying to figure out by installing the VB6.0 code as well as the existing Access and SQL Server databases
Analyzing the Job Work Flow and developing UI flow | 5% | I
Building a Multi-Tenancy Engine for Cloud Options | 2% | I
Building a Security System with Multi-Tenancy Options | 2% | I
Building the Main menu Structure | 2% | I
Building the Sub-Menu Structure | 2% | I
Building Filter Strategy for List pages | 2% | I
Integration Strategy with a Financial API | 10% | I