## Analysis & Plan
Phase (Each Phase 3 months) | Main Module | Sub-Module | Estimation | Developer Comments
Phase I | Security | User Authentication, Roles, Privileges, Groups | 80 | Can use some LDAP open source and integrate it
Phase I | Customers | Receivables, Sales Orders, Quotes, Over the counter Sales, Invoices Multi-Invoices, Customer Types, Payment Types, Credit Memos, Debit Memos, Quote Templates, | 360
Phase I | Vendors | Vendors, Purchase Orders, Consignments, Invoices, Payables, Shipment Settings, Package Settings | 240
Phase I | Company Master | Chart of Accounts, Tax Territories, Rolodex, Divisions, State Tax Settings, Accounting Cycles, | 240
Phase II | Sales Rep | Commissions, Commission Split Types | 120
Phase II | Products Module | Warehousing (In and out), Product Catelog, Product Categories, Product Departments, Order Points, Receive Inventory, Transfer Inventory, Count Inventory, Kit Recipes, Assembly Kits | 400
Phase II | Job Work | Jobs, Bids, Schedule Templates, Submittals, Models | 240
Phase II | Vendor Reports | about 30 reports | 120
Phase II | Finance (Banking) | Banking, General Ledger, Accounts, Journals, | 300
Phase II | Finance Reports | 10 reports | 40
Phase II | Customer Support | Customer Service Requests | 120
Phase III | Dashboard |  | 100 | This should be done right;
Phase III | Customer Reports | About 20 reports | 80 | For Reports, we have to use Jasper Reports or Pentaho Reports to save time
Phase III | Employees | Employees, HR, Payroll | 200
Phase III | Employee Reports | About 20 reports | 80
Phase III | Job Reports | About 30 Reports | 120
Phase III | Taxation | Taxation Reports, 1099, 941 forms, W2, W3 forms and more | 120
Phase III | Company Reports | About 20 reports | 80
Phase IV | Messages | Messaging Integration | 40 | We can use some Messaging API and OS code
Phase IV | Document Module | Company Document Repository | 24 | We can use some open source integration here
Phase IV | Faxes | Fax-Machine Integration | 40 | We can use some Fax API and open source code
Phase IV | Documents | Import Documents | 16
Phase IV | Documents | Link External Documents | 16
3176

## Design
Turbo Pro Approach and Design
Option | Approach/Choices | Team's comments | Pros | Cons
Option 1: Get an Open Source ERP API and build a front-end on it.
| These are some of our choices: OpenBravo http://code.openbravo.com/docs/erp/devel/3.0MP5.3/ (INFO: OpenBravo's front-end is Web 2.0) OR Apache OfBiz http://ci.apache.org/projects/ofbiz/site/javadocs/ (INFO: Apache's OfBiz's front-end is Web 1.0) | There are about 1200 Tables and these products are very comprehensive ERPs geared towards mid-size companies. We would need additional resources, designers to develop based on these API. We need a lot of time understanding these APIs as there are thousands of classes; no documentation other than JavaDocs | These ERP solutions have all the features that we need. If we have the resources to develop. | OpenBravo has a cloud based paid solution; we may have licensing issues. Apache Ofbiz has Apache License. Not sure of the impact. These ERP's come with their own large databases (1200 tables). We also need a complex migration strategy for the current TurboPro Clients
Option 2: Get an OpenSource Finance Module that is Web 2.0 Java based; Develop other modules around it using existing TurboPro Database
| In this option, we will get a Web Based (Web 2.0) Open Source Finance Package; that is simpler than the big ERP packages. (We are not able to find Simple ERP Open Source tools). We can build all other modules around this module so that UI looks similar. Options: http://www.kuali.org/kfs | We have to play with this to know more if this is feasible. The UI in screenshots look very nice; however, we will know more after we have played with the source code. Also, we need the current database of Turbo Pro. | We have a decent Finance Module that has it's own front-end. If we use the existing database, migrating existing clients would be easier. In this option, we see a Kuali HR module also that can be very useful for payroll and HR module | We have to build several other modules from scratch
Option 3: Build a ERP by seeing another ERP made for small businesses in another language;
| http://www.dolibarr.org/ has a simple ERP. However, this is built mainly for European markets. It is developed in PHP. We can build a similar simple ERP by copying their screens and building it in JSP/jQuery. And possibly integrate a Financial Open Source API. jGnash has a simple Financial Ledger API. Does not have commercial strength one. However, we can try our best. |  | We can save time in UI Design. | We are not sure of the integration challenges with jGNash API. It does not use any SQL Database, it uses XML files for database. jGnash also does not have business ledgers; only simple personal finance ledgers; we have to customize.
Option 4: Build an ERP and then Integrate into a commercial Finance Product
| We can build a new product using the old database. Web UI. For Finance API, we can use commercial tool like Quickbooks. |  | Will save time compared to the other options. | Quickbooks licensing issues may come in the way: Their SDK/API, critical information 1. IF We are going to offer Cloud based Solutions that is integrated with Quickbooks, this is NOT allowed by Quickbooks as they want us to use their Hosted Quickbooks Version. https://ipp.developer.intuit.com/sdk/qb/Get_Oriented 2. IF we are going to offer only Client/Server based solution, we can integrate with Quickbooks as long as: a. We include their logo in our product b. And purchase a license of their product for each installation